## Tabelle1
System | Page/function |  | Start day | End day | Owner | Status
HK Secure site | Personal details | Front end |  | 10.24 | Susan | In progress
|  | Back end |  | 10.23 | Alan | Finished
|  | SIT | 10.25 | 11.13 | Nora | Don't start
| CRS update page | Front end | 10.21 | 11.8 | Bill | In progress
|  | Back end |  | 10.23 | Alan | Finished
|  | SIT | 10.25 | 11.13 | Nora | Don't start
| Smart form | Development | 10.25 | 10.28 | Dapeng | Don't start
|  | SIT | 10.25 | 11.13 | Nora | Don't start
CRMT | Update address | development |  | 11.1 | Rain | In progress
|  | SIT | 11.08 | 11.21 | Qianqian | Don't start
| CRS information | development |  | 11.1 | Rain | In progress
|  | SIT | 11.08 | 11.21 | Qianqian | Don't start
| Smart form | Development | 10.8 | 10.29 | Nicole | In progress
|  | SIT | 11.08 | 11.21 | Qianqian | Don't start
DSO-EE | Smart form | Development | 10.25 | 10.29 | Dapeng | Don't start
| ERL（KYC, CRS） | Front end |  | 10.23 | Kevin | Finished
|  | SIT | 10.25 | 11.07 | Qianqian | Don't start
| EEVC | SIT | 10.25 | 11.07 | Qianqian | Don't start
| PM(KYC) | Front end |  | 10.29 | Kevin | Don't start
|  | SIT | 10.25 | 11.07 | Qianqian | Don't start
| PA+PM(KYC,CRS) | Front end |  | 10.29 | Kevin | Don't start
|  | SIT | 10.25 | 11.07 | Qianqian | Don't start
DSO-ER | Smart form | Development | 11.11 | 11.14 | Dapeng | Don't start
| ERL（KYC, CRS） | SIT | 11.14 | 11.27 | Nora | Don't start
| EEVC | SIT | 11.14 | 11.27 | Nora | Don't start
| PM(KYC) | SIT | 11.14 | 11.27 | Nora | Don't start
| PA+PM | SIT | 11.14 | 11.27 | Nora | Don't start
DC APP (IOS & Android) | ERL（KYC, CRS） | SIT | 11.1 | 11.14 | Tracy | Don't start
| EEVC | SIT | 11.1 | 11.14 | Tracy | Don't start
| PM(KYC) | SIT | 11.1 | 11.14 | Tracy | Don't start
| PA+PM | SIT | 11.1 | 11.14 | Tracy | Don't start
Public site | ERL（KYC, CRS） | SIT | 11.15 | 11.28 | Tracy | Don't start
| EEVC | SIT | 11.15 | 11.28 | Tracy | Don't start
| PM(KYC) | SIT | 11.15 | 11.28 | Tracy | Don't start
| PA+PM | SIT | 11.15 | 11.28 | Tracy | Don't start
Employer site |  | Development | 11.11 | 11.15 | Komla | Don't start
|  | SIT | 11.22 | 11.26 | Qianqian | Don't start